## Sheet1
PLAN | PCB DESIGN | STM32 CODE | WiFi TELEMETRY
24/02/2026 - 01/03/2026 | Verification for already designed pcb | Modification in existing code for communication and locomotion stage-1 | Get the developed software from seniors and gothrough the software
02/03/2026 - 08/03/2026 | Start designig next pcb based on priority | Develop pre-required drivers and functions | Modify the existing software
| - | Convert ESP Code to STM32 | Test modified software in bot
09/03/2026 - 15/03/2026 | Continue 2nd pcb design and finalize the design | Develop required drivers and functions | -
| - | Convert ESP Code to STM32 | -
| - | Try to get the reset information from stm32 and make it visible in software | -